TECHNICAL & FINANCIAL PROPOSAL

Development of Production Management System (PMS)

Bangladesh Industrial Technical Assistance Centre (BITAC)

| Submitted By | Technocrats |
| --- | --- |
| Submitted To | Bangladesh Industrial Technical Assistance Centre (BITAC) |
| Reference | ToR: Development of Production Management System (PMS) – BITAC |
| Proposal Date | 31 March 2025 |
| Project Duration | 2 (Two) Months from contract signing |

Technocrats

# Executive Summary

Technocrats proposes to design, develop, test, and deploy a Production Management System (PMS) for BITAC within two months at a total cost of BDT 12,00,000/- (Twelve Lakh Taka), exclusive of VAT and taxes. This proposal reflects a revised scope incorporating client-specified adjustments.

### Scope Summary

|  | This is Proposal v2.0. Scope changes from the original ToR are highlighted throughout this document. |
| --- | --- |

| Item | Original Scope | Revised Scope |
| --- | --- | --- |
| Invoice & Payment | Full invoice + payment tracking | Invoice generation only — payment collection not included |
| IMS Integration | Full bi-directional sync (stock, issuance, return) | Limited: product availability + raw material demand check against a job only |
| Procurement / Purchase | Not in ToR | Explicitly excluded — confirmed out of scope |
| Customer Panel | Not in original scope | Added — real-time work order progress visibility for clients |

### Modules in Scope

- System Architecture and Infrastructure Setup

- User Management and Role-Based Access Control

- Contract, Quotation, and Work Order Management

- MRP and Operation Sheet Management

- Work Center Scheduling with Gantt Chart

- Shop Floor Execution and Real-Time WIP Tracking

- Quality Control, Inspection, and NCR Management

- Delivery, Logistics, and Challan Generation

- Invoice Generation (up to invoice issuance)

- IMS Integration — Product Availability + Raw Material Demand Check

- Customer Panel — Real-Time Work Order Visibility

- Reporting and Analytics Dashboards

- System Testing, UAT, and Deployment

### Financial Summary

| Item | Amount (BDT) |
| --- | --- |
| Total Contract Value | 12,00,000/- |
| VAT / Tax | As applicable — excluded from above |
| Training | 2 Personnel of BITAC ICT Division |
| Contract Duration | 2 (Two) Calendar Months |
| Warranty Period | 3 Months post-delivery (bug fixes only) |

# Company Profile

## 3.1 About Technocrats Digital

Technocrats Digital is a Bangladesh-based technology firm specializing in enterprise web application development, digital transformation, and IT consulting. Our team of experienced full-stack developers, integration engineers, and business analysts delivers purpose-built software solutions for government institutions, industrial organizations, and private sector enterprises across Bangladesh.

## 3.2 Core Competencies

| Domain | Capabilities |
| --- | --- |
| Backend Development | PHP (Laravel), RESTful API design, OAuth 2.0/JWT, MySQL, Redis |
| Frontend Development | React.js, Vue.js, Next.js, TailwindCSS, responsive web interfaces |
| System Integration | IMS/ERP API integration, third-party platform connectivity, webhook design |
| Customer Portals | Real-time dashboards, client self-service panels, notification engines |
| Security Engineering | RBAC, 2FA/MFA, TLS, field-level encryption, OWASP compliance |
| DevOps | Docker, Git/GitHub, CI/CD, VPS and cloud server management (Coolify, Nginx) |
| Government/Institutional | Prior BITAC HR/Finance systems, provident fund, leave management, ledger reports |

## 3.3 Relevant Experience with BITAC

Technocrats Digital has existing experience developing institutional management software for BITAC, including PHP-based HR systems, provident fund report generation, leave management with Bangla PDF output (mPDF), accounting voucher and ledger systems, and management reporting modules. This institutional familiarity significantly reduces discovery time and enables faster, more accurate system design for the PMS.

# Understanding of Requirements

## 4.1 Current Operational Gaps

BITAC currently manages its production operations through manual workflows and a standalone IMS. Key gaps that the PMS will address:

- No unified order lifecycle system from RFQ through delivery and invoice

- Manual quotation templates with no automated approval chain or audit trail

- No real-time shop-floor visibility for supervisors or management

- Material availability not verified against job demand before production starts

- QC inspections are paper-based with no digital NCR tracking

- Clients have no visibility into the progress of their orders

- Delivery documents generated manually, causing delays

- Invoice preparation is disconnected from delivery confirmation

## 4.2 Production Workflow — End-to-End Mapping

The following table maps each step of the production workflow to the corresponding PMS module, including the revised scope for each item in this proposal:

| # | Workflow Stage | Business Function | PMS Module (Scope) |
| --- | --- | --- | --- |
| 1 | RFQ Submission | Client or staff submits request for quotation via portal or manual entry | Contract & Quotation Mgmt |
| 2 | Quotation Preparation | Cost templates, VAT calculation, version control, validity period | Sales Quotation Module |
| 3 | Multi-Level Approval | Configurable approval chain with digital signatures and audit trail | Approval Workflow |
| 4 | Work Order Generated | One-click conversion of approved quotation to uniquely identified work order | Work Order Management |
| 5 | IMS Check | Verify product stock availability; calculate raw material demand for this job against IMS | IMS Integration (Limited) |
| 6 | MRP + Operation Sheets | BOM-based material calculation, material requisition notes, sequential operation sheets with QR | Production Planning |
| 7 | Work Center Scheduling | Gantt-based scheduling across machines and shifts; conflict detection alerts | Scheduling Module |
| 8 | Shop Floor Execution | Real-time job tracking, WIP logging, downtime recording; supervisor dashboard | Shop Floor Control |
| 9 | QC Inspection | Configurable checklists, pass/fail logging, defect categorization, QC hold enforcement | Quality Control |
| 10 | NCR + Rework (Fail) | Non-conformance report, rework order, re-enters shop floor with traceability to original job | NCR & Rework |
| 11 | Delivery + Challan | Auto-generation of delivery challan, packing list, gate pass; proof of delivery capture | Delivery & Logistics |
| 12 | Invoice Generation | Invoice auto-generated on delivery confirmation; VAT/discount applied; PDF issued | Invoice Module (Limited) |
| 13 | Customer Panel | Customer logs in to see real-time status of their work order at every stage — from production to delivery | Customer Panel |

## 4.3 End-to-End Production Workflow Diagram

The diagram below illustrates the complete production management workflow implemented in the PMS — from initial RFQ submission through production planning, shop floor execution, quality control, delivery, and invoice generation. Colour coding identifies each operational department. Decision points (diamonds) represent the quotation approval gate and the QC pass/fail gate, with branch paths for revision and rework respectively.

Figure 1: BITAC PMS — End-to-End Production Management Workflow

# Technical Approach and Methodology

## 5.1 System Architecture

| Layer | Technology | Purpose | Justification |
| --- | --- | --- | --- |
| Frontend | React.js + TailwindCSS | Responsive UI + Customer Panel | Component reuse, real-time state management |
| Backend (API) | PHP — Laravel Framework | Business logic, RESTful APIs | Secure, proven in BD institutions |
| Database | MySQL 8.x | Structured data management | Reliable, cost-effective RDBMS |
| Authentication | OAuth 2.0 / JWT | Staff + customer secure sessions | Industry-standard; separate token scopes |
| Real-time Events | Laravel Echo + Pusher/WebSocket | Customer Panel live updates | Push notifications to customer browser |
| Cache Layer | Redis | Performance optimization | Fast response, reduce DB load |
| IMS Integration | RESTful API (JSON) — Read-only queries | Material availability checks | Lightweight, no write-back to IMS |
| Version Control | Git / GitHub | Source code management | CI/CD integration, full history |

## 5.2 IMS Integration — Revised Scope Detail

| SCOPE NOTE | IMS integration is read-only in this proposal. PMS queries IMS for two specific data points only. No material issuance confirmation, no return processing, no inventory write-back, and no procurement or purchase order integration. |
| --- | --- |

| IMS Query Type | Description |
| --- | --- |
| Product Availability Check | Before a work order is accepted into production, PMS queries IMS to verify whether the required finished product (or semi-finished component) is already available in stock. If stock exists, the system alerts the planner to avoid duplicate production. |
| Raw Material Demand Check | Once a work order is approved and BOM is defined, PMS calculates raw material quantities (with wastage allowance) and queries IMS for current stock levels of each required material. If any material is below the required quantity, a shortage alert is displayed on the MRP screen for action by the stores/planning team. |
| NOT included in IMS scope | material return flows, inventory transaction write-back, supplier/vendor data, purchase requisitions, purchase orders — all explicitly out of scope for this proposal. |

## 5.3 Customer Panel — Design Approach

The Customer Panel is a dedicated, separately branded web portal through which BITAC's clients can log in and track the real-time status of their work orders. It is built on the same backend as the PMS but uses a restricted authentication scope — customers can only view data related to their own orders and cannot access any internal operational screens.

### Real-Time Visibility Architecture

- Customer logs in using credentials issued by BITAC (separate from staff login)

- On login, the customer sees a dashboard of all their active and past work orders

- Each work order shows a live progress indicator: Quotation Accepted → In Production → QC → Ready for Delivery → Delivered

- Real-time push notifications via WebSocket: browser tab updates automatically without page refresh when job status changes

- Production milestone alerts: customer receives email/SMS when their job moves to each key stage

- QC result notification: customer is notified when their job passes QC inspection

- Estimated delivery date displayed, updated dynamically from the scheduling module

- Invoice download: when the invoice is generated after delivery, the customer can download it from their panel

- Complaint and feedback submission linked to their work order for BITAC admin action

## 5.4 Security Architecture

| Control | Implementation |
| --- | --- |
| Staff Authentication | Username + password with optional 2FA (TOTP); JWT with expiry and refresh rotation |
| Customer Authentication | Separate JWT scope; credentials issued by BITAC Admin; customers cannot access staff routes |
| Authorization | RBAC at module/screen/field level for staff; read-only restricted scope for customers |
| Transport Security | All traffic TLS 1.2+ / HTTPS; no plain HTTP on any route |
| Data Isolation | Customer queries are scoped to their own customer_id at database query level — no data leakage possible |
| Audit Trail | All data modifications logged with user ID, role, timestamp, old/new values |
| XSS / CSRF | Laravel CSRF tokens; React output escaping; content security policy headers |
| Account Lockout | Auto-lockout after 5 failed login attempts; separate lockout policy for customer vs staff accounts |
| Backup | Daily automated database backup; retained for 30 days minimum |

# Detailed Scope of Work by Module

The table below defines the precise feature-level scope for all 13 modules. Exclusions are explicitly stated per module to avoid ambiguity.

| Module | Features Included | Explicit Exclusions |
| --- | --- | --- |
| 1. System Architecture & Infrastructure | ✔ Dev/staging/production environment ✔ MySQL schema (all modules) ✔ Laravel API scaffold ✔ Git/CI-CD pipeline ✔ HTTPS/TLS configuration ✔ Staff + customer auth layers | ✘ Hosting hardware procurement ✘ SSL certificate cost |
| 2. User Management & Security | ✔ RBAC — 10 staff roles (Admin, Supervisor, Operator, QC, Finance, etc.) ✔ Customer role (separate scope) ✔ 2FA for sensitive staff roles ✔ Session management, auto-logout ✔ Audit trail for all data changes | ✘ Biometric or hardware token integration |
| 3. Contract, Quotation & Work Order | ✔ RFQ capture (portal + internal entry) ✔ Quotation templates with cost formula (material + labor + overhead + VAT) ✔ Multi-level approval with digital signature ✔ Work order auto-generation from approved quotation ✔ Version control for quotations and WOs ✔ Email notifications to client on approval | ✘ Advanced CRM or sales pipeline ✘ Third-party e-signature platform integration |
| 4. MRP + Operation Sheets | ✔ BOM management ✔ Automatic material quantity calculation (with wastage allowance) ✔ IMS stock check (shortage alert — see Module 10) ✔ Material Requisition Note generation for shortages ✔ Operation sheet creation (sequential steps, machines, operators) ✔ QR/barcode on operation sheets for shop-floor retrieval | ✘ Automated purchase order from MRP ✘ Supplier selection from MRP |
| 5. Work Center Scheduling | ✔ Work center definitions (Machine Shop, Heat Treatment, Fabrication, Welding, Assembly) ✔ Shift pattern configuration (single/double/overtime) ✔ Drag-and-drop Gantt chart ✔ Machine conflict detection alerts ✔ Machine downtime schedule integration | ✘ Predictive maintenance AI ✘ IoT machine sensor integration |
| 6. Shop Floor Execution & WIP | ✔ Touchscreen-optimized operator terminal ✔ Start/stop time recording per operation ✔ Quantity completed and rejected with reason codes ✔ Downtime event logging (machine, material, operator, power) ✔ WIP dashboard with color-coded job progress ✔ Real-time alerts (shortage, QC ready, completion) | ✘ IoT/OPC-UA machine data capture |
| 7. QC, Inspection & NCR | ✔ Configurable inspection checklists per product and stage ✔ Pass/fail logging with dimensional measurement ✔ Defect categorization and code library ✔ NCR creation and corrective action tracking ✔ QC hold enforcement before job progression ✔ Rework order from NCR with traceability to original job | ✘ Statistical Process Control (SPC) charts (future phase) ✘ External lab test integration |
| 8. Delivery, Logistics & Challan | ✔ Delivery scheduling and dispatch planning ✔ Auto-generation: delivery challan, packing list, gate pass ✔ E-signature or photographic proof of delivery ✔ Post-delivery complaint ticket linked to work order | ✘ Transport/vehicle management ✘ Third-party courier API integration |
| 9. Invoice Generation | ✔ Invoice auto-generated on delivery confirmation ✔ VAT and discount handling on invoices ✔ Invoice PDF with BITAC letterhead ✔ Invoice linked to work order and delivery challan ✔ Invoice status: Draft, Issued, Acknowledged ✔ Invoice accessible by customer from their panel ✔ Invoice archival in document store | ✘ Payment collection recording ✘ Payment reminders and overdue tracking ✘ Accounts receivable ledger ✘ Bank reconciliation |
| 10. IMS Integration (Limited) | ✔ Product availability check: query IMS stock for finished/semi-finished items before production ✔ Raw material demand check: query IMS material stock levels against job BOM quantities ✔ Shortage alert on MRP screen if material below required quantity ✔ Read-only API queries to IMS — no write-back | ✘ Material issuance confirmation ✘ Material return flows ✘ Inventory write-back or transaction posting ✘ Procurement, purchase requisitions, purchase orders ✘ Vendor/supplier data exchange |
| 11. Customer Panel (NEW) | ✔ Customer login with dedicated credentials (BITAC-issued) ✔ Work order dashboard: all active and past orders for this customer ✔ Real-time status indicator: Quotation Accepted → In Production → QC → Ready for Delivery → Delivered ✔ WebSocket push updates: live status change without page refresh ✔ Email + SMS notification on each milestone change ✔ QC pass/fail notification ✔ Estimated delivery date (from scheduling module) ✔ Invoice download when issued ✔ Feedback and complaint submission linked to work order | ✘ Customer quotation self-editing ✘ Online payment gateway ✘ Customer CRM or account management |
| 12. Reporting & Analytics | ✔ Role-specific KPI dashboards (Production, QC, Management) ✔ KPIs: production efficiency, lead time, rejection rate, order fulfillment ✔ Custom report builder with date range and status filters ✔ Data export: Excel, CSV, PDF | ✘ Predictive analytics and ML forecasting (future phase) |
| 13. Testing, UAT & Deployment | ✔ Unit testing (PHPUnit backend, Jest frontend) ✔ Integration testing (all module-to-module flows and IMS queries) ✔ UAT support with BITAC staff using real operational data ✔ OWASP security vulnerability scan ✔ Performance test (100+ concurrent users) ✔ Production deployment on BITAC's designated server ✔ User and administrator manuals (English) ✔ Source code handover (GitHub transfer + zipped archive) | ✘ Training delivery (excluded from this engagement) ✘ Bangla manual (available as optional add-on) |

# Proposed Team Structure

| # | Role | Allocation | Responsibilities |
| --- | --- | --- | --- |
| 1 | Project Manager | Full-time — 2 months | Stakeholder liaison, sprint planning, milestone reporting, risk management, BITAC coordination |
| 2 | Senior Backend Developer | Full-time — 2 months | Core API, database schema, RBAC, IMS integration, business logic, Laravel architecture |
| 3 | Backend Developer | Full-time — 2 months | Module development (QC, Delivery, Invoice, Reporting), unit tests, Customer Panel API |
| 4 | Frontend Developer | Full-time — 2 months | React.js UI for all staff modules, Customer Panel frontend, Gantt chart, WebSocket real-time updates |
| 5 | Integration & QA Engineer | Full-time — 2 months | IMS API queries, end-to-end testing, UAT, OWASP scan, deployment, performance testing |

# Project Timeline — 2 Months (8 Weeks)

MONTH 1 — Development Phase: Weeks 1–4

| Week | Focus | Modules / Tasks Delivered | Milestone |
| --- | --- | --- | --- |
| Week 1 | Infrastructure + User Mgmt + Quotation start | Server/environment setup, DB schema, Git/CI-CDUser Management, RBAC, 2FA, audit trailRFQ capture, Quotation template engine | All user roles working with RBAC |
| Week 2 | Quotation completion + Work Order + Customer Portal (login) | Approval workflow, digital signaturesWork order auto-gen, version controlCustomer portal login + basic dashboard scaffolding | End-to-end RFQ → Work Order flow signed off |
| Week 3 | MRP + Operation Sheets + IMS Queries | BOM management, MRP calculation with wastageOperation sheet creation, QR/barcode generationIMS product availability query + material demand checkShortage alert on MRP screen | MRP generates correct requisitions + IMS check live |
| Week 4 | Scheduling + Shop Floor + Customer Panel (live status) | Work center Gantt chart (drag-and-drop)Shop floor terminal, WIP dashboard, downtime loggingCustomer Panel: real-time job status + WebSocket push updates | MILESTONE 1: Live WIP + Customer Panel shows real-time status |

MONTH 2 — QC, Delivery, Invoice & Go-Live: Weeks 5–8

| Week | Focus | Modules / Tasks Delivered | Milestone |
| --- | --- | --- | --- |
| Week 5 | QC + NCR + Rework | QC inspection checklists (configurable per product)Pass/fail logging, defect codes, NCR creationRework order from NCR with traceabilityQC hold enforcement before job progressionCustomer Panel: QC pass notification pushed to customer | QC hold enforced; rework traceable to original job |
| Week 6 | Delivery + Invoice + Customer Panel (complete) | Challan, packing list, gate pass auto-generationProof of delivery (e-signature/photo)Invoice auto-generation on delivery (VAT, PDF, letterhead)Customer Panel: delivery notification + invoice downloadCustomer Panel: feedback/complaint submission | Invoice generated on delivery; customer sees it live |
| Week 7 | Reporting + UAT + Security Audit | KPI dashboards (Production, QC, Management)Custom report builder, Excel/CSV/PDF exportUAT with BITAC staff on real operational dataOWASP security scan, performance test (100+ concurrent users) | MILESTONE 2: UAT passed; zero critical defects |
| Week 8 | Deployment + Handover | Production deployment on BITAC serverUser and administrator manuals (English)Source code + admin credentials handoverGitHub private repository transfer | FINAL: Deployment live; formal acceptance signed |

# Financial Proposal

## 9.1 Module-wise Cost Breakdown

The total contract value is BDT 12,00,000/- (Twelve Lakh Taka Only), exclusive of VAT and taxes. The cost reflects the revised scope: training excluded, invoice module limited to generation, IMS integration limited to two read-only query types, and Customer Panel added as a new module.

| # | Module | Scope Note | Cost (BDT) |
| --- | --- | --- | --- |
| 1 | System Architecture & Infrastructure | Environment, DB, CI/CD, HTTPS, auth layers | 1,00,000 |
| 2 | User Management & Security | 10 staff roles + customer role, RBAC, 2FA | 80,000 |
| 3 | Contract, Quotation & Work Order | RFQ, templates, approval, WO auto-gen | 1,50,000 |
| 4 | MRP + Operation Sheet Management | BOM, material calc, QR sheets, requisitions | 1,60,000 |
| 5 | Work Center Scheduling (Gantt) | Gantt, shift config, conflict detection | 1,00,000 |
| 6 | Shop Floor Execution & WIP Tracking | Terminal UI, WIP dashboard, OEE data | 1,10,000 |
| 7 | QC, Inspection & NCR Management | Checklists, defects, NCR, rework, QC hold | 1,00,000 |
| 8 | Delivery, Logistics & Challan | Challan, gate pass, POD capture | 75,000 |
| 9 | Invoice Generation (limited) | Auto-invoice up to issuance; PDF, VAT only | 50,000 |
| 10 | IMS Integration (limited — read-only) | Product availability + raw material demand | 60,000 |
| 11 | Customer Panel (real-time) | NEW: live WO status, push notifications, invoice download | 75,000 |
| 12 | Reporting & Analytics Dashboards | KPI dashboards, custom reports, exports | 75,000 |
| 13 | Testing, UAT & Deployment | Unit/integration/security/UAT, deploy, manuals (EN) | 65,000 |
|  | TOTAL CONTRACT VALUE (Excluding VAT/Tax) |  | 12,00,000/- |

## 9.2 Payment Schedule

| # | Payment | Milestone / Trigger | Condition | % | Amount (BDT) |
| --- | --- | --- | --- | --- | --- |
| 1 | Advance | On contract signing | Signed contract received by Technocrats Digital | 30% | 3,60,000 |
| 2 | Milestone 1 | End of Week 4 | RFQ→WO flow + IMS queries live + Customer Panel real-time status verified by BITAC | 30% | 3,60,000 |
| 3 | Milestone 2 | End of Week 7 | UAT passed with zero critical defects; security scan clean; invoice generation demo accepted | 25% | 3,00,000 |
| 4 | Final | End of Week 8 | Production deployment live; manuals delivered; source code handed over; formal acceptance certificate signed | 15% | 1,80,000 |
|  | TOTAL |  |  | 100% | 12,00,000/- |

## 9.3 Cost Exclusions

| Item | Clarification |
| --- | --- |
| VAT / Tax | Excluded. Applicable taxes charged separately per NBR regulations. |
| Training | Explicitly excluded from this engagement. Available as a separate add-on engagement. |
| Payment collection & receivables | Invoice module covers generation and issuance only. Full AR/payment tracking is a future phase. |
| IMS write-back / transactions | IMS integration is read-only. No material issuance, returns, or inventory posting included. |
| Procurement / Purchase Orders | Explicitly out of scope — confirmed by client. |
| Bangla user manual | English manual included. Bangla version available as optional add-on at BDT 20,000. |
| SMS gateway credits | Architecture supports SMS notifications. Gateway credit cost borne by BITAC. |
| Hosting infrastructure | BITAC bears cost of server/NDC hosting. Vendor deploys on BITAC's designated infrastructure. |
| Post-warranty support | 3-month bug-fix warranty included. Extended maintenance contracts quoted separately. |

# Deliverables

| # | Deliverable | Format | When |
| --- | --- | --- | --- |
| 1 | Fully functional PMS — all 13 modules | Live hosted application | Week 8 |
| 2 | Customer Panel (real-time portal) | Live URL with customer login | Week 6 |
| 3 | Database schema and ER diagram | PDF + SQL schema export | Week 1 |
| 4 | API documentation | Postman collection + PDF | Week 4 |
| 5 | IMS integration — query module + test report | Code + integration test results | Week 3 |
| 6 | Unit and integration test reports | HTML/PDF test output | Week 7 |
| 7 | OWASP security scan report | PDF checklist | Week 7 |
| 8 | UAT report with BITAC sign-off | Word document + sign-off sheet | Week 7 |
| 9 | User manual (English) | PDF + Word | Week 8 |
| 10 | Administrator guide (English) | PDF + Word | Week 8 |
| 11 | Source code handover package | GitHub repo transfer + zipped archive | Week 8 |
| 12 | Admin credentials and config documentation | Sealed envelope + encrypted digital copy | Week 8 |
| 13 | Formal acceptance certificate | Signed by BITAC committees | Week 8 |

# Acceptance Criteria

| Criterion | Specification |
| --- | --- |
| Functional completeness | All 13 modules functional per scope; UAT passed without critical defects |
| IMS integration | Product availability check and raw material demand check verified with 100% accuracy against test data |
| Customer Panel | Real-time status push confirmed working in browser; email/SMS milestone alerts received by test customer |
| Invoice generation | Invoice auto-generated on delivery confirmation; PDF correctly formatted with VAT |
| Performance | API response time under 2 seconds; 100+ concurrent users supported |
| Security | OWASP scan complete; no high-risk vulnerabilities; HTTPS enforced; customer data isolation verified |
| Documentation | English user and admin manuals delivered and reviewed by BITAC |
| Deployment | System live on BITAC production server; accessible by all authorized staff and customers |
| Sign-off | Formal acceptance certificate signed by Operation Review Committee and IT Audit Committee |

# Terms and Conditions

## 12.1 General

- Proposal valid for 90 days from submission date.

- Contract commences within 7 working days of signed agreement.

- Total duration: 2 calendar months from effective start date.

- Training is excluded. A separate training engagement can be quoted on request.

- All source code, documentation, and deliverables become exclusive property of BITAC upon final payment.

## 12.2 Warranty

- 3-month bug-fix warranty from final acceptance date.

- Critical bugs: resolved within 24 hours. Major bugs: 48 hours. Minor bugs: 5 working days.

- Warranty excludes new feature requests, scope additions, and issues caused by unauthorized third-party modifications.

## 12.3 Client Responsibilities

- BITAC designates a Project Coordinator with authority to approve deliverables within 3 working days.

- BITAC provides IMS API documentation within 7 days of contract signing.

- BITAC provides production server access by Week 6 for deployment preparation.

- BITAC designates staff for UAT participation in Week 7.

- BITAC issues customer portal credentials to end-clients for UAT testing of the Customer Panel.

## 12.4 Change Management

- Scope changes require written Change Request (CR) from BITAC.

- Each CR assessed for cost and timeline impact within 3 working days.

- Approved CRs priced separately and attached as contract addendum.

## 12.5 Governing Law

- Governed by the laws of the People's Republic of Bangladesh.

- Disputes resolved by mutual negotiation first; if unresolved, via Bangladesh Arbitration Act 2001.

# Declaration and Signature

We, Technocrats Digital, declare that the information in this proposal is accurate, that we have read and accepted the Terms of Reference, and that we are authorized to enter into this contract.

| FOR TECHNOCRATS DIGITAL _________________________________ Authorized Signatory Name: ____________________________ Designation: ______________________ Date: _____________________________ Seal: | FOR BITAC (CLIENT ACCEPTANCE) _________________________________ Authorized Signatory Name: ____________________________ Designation: ______________________ Date: _____________________________ Seal: |
| --- | --- |

— End of Proposal —

Technocrats Digital  |  Dhaka, Bangladesh  |  Confidential  |  v2.0